## SCADATable
ID | Project Name | Company/Project | Type | Engineer1 | Engineer2 | TFC | StartDate | EndDate | IFS | Network | Graphics | P2P | Status | Service Charge Ex.TDS | Service Charge Inc.TDS | TDS @1.5% | VAT @13% | Service Charge Inc.VAT | Informed Date | Amount Deposited? | Deposited Date | Final Bill Issued? | Remarks
1 | Middle Modi(18MW) | Middle Modi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-04-25 | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-02 | NO |  | NO
2 | Nilgiri 2 (71MW) | Nilgiri Khola Hydropower Company Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  | 2024-04-03 | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-26 | YES | 2025-02-03 | NO
3 | Ghar Khola (14 MW) | Myagdi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-06-03 | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-26 | YES | 2025-02-07 | NO
4 | Upper Chameliya (40MW) | Api Chameliya Power Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-24 | YES | 2025-02-03 | NO | only 1500000
5 | Likhu 1 | Pan Himalaya Energy Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3602000 | 3656852.7919 | 54852.7919 | 475390.8629 | 4132243.6548 | 2024-12-31 | YES | 2025-02-11 | NO
6 | Upper Kalangagad (38MW) | Sanigad Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2024-12-31 | NO |  | NO
7 | Upper Sanigad(10.7MW) | Bungal Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
8 | Kalanga(15MW) | Kalanga Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
9 | Super Madi(44MW) | Super Madi Hydropower Limited | Powerhouse | Er. Janardan Rimal |  |  |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-03 | NO |  | NO
10 | Upper Tamakoshi(456MW) | Upper Tamakoshi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 5352000 | 5433502.5381 | 81502.5381 | 706355.3299 | 6139857.868 | 2025-01-02 | NO |  | NO
11 | Lower Modi (20MW) | Modi Energy Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-05-09 | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-26 | NO |  | NO
12 | Upper Balefi(36MW) | Balefi Hydropower Limited | Powerhouse | Er. Sumit Sah |  | 0 |  | 2024-06-24 | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-02 | YES | 2025-01-25 | NO
13 | Maya Khola (14MW) | Maya Khola Hydropower Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-07 | NO |  | NO
14 | Nilgiri 1 | Nilgiri Khola Hydropower Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-31 | YES | 2025-02-03 | NO
15 | Middle Tamor(73MW) | Sanima Middle Tamor Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-08-29 | TRUE | TRUE | TRUE | TRUE | Completed | 3602000 | 3656852.7919 | 54852.7919 | 475390.8629 | 4132243.6548 | 2024-12-26 | NO |  | NO
16 | Upallo Khimti (12MW) | Himalay Urja Bikas Company Limited | Powerhouse | Er. Sumit Sah |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | YES | 2025-02-03 | NO
17 | Matatirtha 220kV |  | Substation | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 7102000 | 7210152.2843 | 108152.2843 | 937319.797 | 8147472.0812 | 2025-01-09 | NO |  | NO
18 | New Khimti 220kV |  | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed |  | 0 | 0 | 0 | 0 |  | NO |  | NO
19 | New Hetauda 220kV | Nepal India Power Transmisson and Trade Project | Substation | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 4602000 | 4672081.2183 | 70081.2183 | 607370.5584 | 5279451.7766 | 2025-01-10 | NO |  | NO
20 | Tallo Khare(11MW) | Universal Power Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | NO |  | NO
21 | Arun 3 ,Dhalke 400kV Extension | SJVN Arun-3 Power Development Company Pvt Ltd | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-09-25 | TRUE | TRUE | TRUE | TRUE | Completed | 3250000 | 3299492.3858 | 49492.3858 | 428934.0102 | 3728426.3959 | 2025-01-11 | NO |  | NO
22 | Mathillo Mailung(14.3MW) | Mathillo Mailun Khola Jalvidhyut Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | YES | 2025-02-24 | NO
23 | Seti Nadi (25MW) | Vision Lumbini Urja Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-11-24 | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | YES | 2025-02-21 | NO
24 | Loharpatti | Dhalkebar Loharpatti 132kV Transmission line Project | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  | 2025-01-27 | TRUE | TRUE | TRUE | TRUE | Completed | 3852000 | 3910659.8985 | 58659.8985 | 508385.7868 | 4419045.6853 | 2025-01-10 | NO |  | NO
25 | Udipur | Marshyangdi Corridor 220kV TL Project | Substation | Er. Ram Sharan Timilsina |  | 0 | 2024-11-24 |  | TRUE | TRUE | TRUE | TRUE | Completed | 5602000 | 5687309.6447 | 85309.6447 | 739350.2538 | 6426659.8985 | 2025-01-09 | NO |  | NO
26 | Inaruwa 220kV | Nepal India Power Transmisson and Trade Project | Substation | Er. Sumit Sah |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-10 | NO |  | NO
27 | Dudhkunda(12MW) | Mount Everest Power Development Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | YES | 2025-02-20 | NO
28 | Dordi 1(12MW) | Dordi Khola Jalavidhyut Compani Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
29 | Upper Solu(19.8MW) | Beni Hydropower Project Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2024-12-26 | YES | 2025-02-13 | NO
30 | Tamghas 132kV | Burtibang- Paudi Amarai- Tamghas- Sandhikharka- Gurusinghe 132kV TL Project | Substation | Er. Neha Karn | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-09 | NO |  | NO
31 | Trishuli 3B 220kV |  | Substation | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-09 | NO |  | NO
32 | Chilime Hub 220kV |  | Substation | Er. Ram Sharan Timilsina |  | 0 | 2024-11-28 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 5102000 | 5179695.4315 | 77695.4315 | 673360.4061 | 5853055.8376 | 2025-01-09 | NO |  | NO
33 | Sanjen (42.5MW) | Sanjen Jalvidyut Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 | 2024-12-08 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-13 | YES | 2024-12-17 | NO
34 | Sanjen Upper (14.8MW) | Sanjen Jalvidyut Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 | 2024-12-08 | 2024-12-23 | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-13 | YES | 2024-12-17 | NO
35 | New Bharatpur 220kV | Marshyangdi Corridor 220kV TL Project | Substation | Er. Sumit Sah |  | 0 | 2024-12-17 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-09 | NO |  | NO
36 | Rasugadhi(111MW) | Rasuwagadhi Hydropower Company Limited | Powerhouse | Er. Sumit Sah |  | 0 | 2024-12-31 | 2025-01-07 | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2024-12-26 | YES | 2024-12-31 | NO
37 | DownPiluwa (10.3MW) | River Falls Power Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-01-07 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-10 | YES | 2025-01-21 | NO
38 | SuperNyadi(40.27MW) | Siuri Nyadi Power Limited | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned | 2602001 | 2641625.3807 | 39624.3807 | 343411.2995 | 2985036.6802 | 2024-12-10 | NO |  | NO
39 | Langtang(20MW) | Multi Energy Development P. Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-02-11 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602002 | 2641626.3959 | 39624.3959 | 343411.4315 | 2985037.8274 | 2024-12-10 | NO |  | NO
40 | Mathillo Mardi(7)+ Mardi(4.8MW) | United IDI Mardi and RB Hydropower Ltd | Powerhouse | Er. Ram Sharan Timilsina |  |  |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 250000 | 253807.1066 | 3807.1066 | 32994.9239 | 286802.0305 |  | NO |  | NO
41 | Garjyang Bay at New Khimti | Ramechhap-Garjyang-Khimti 132kV TL Project | Substation |  |  |  |  | 2024-11-24 | TRUE | TRUE | TRUE | TRUE | Completed | 500000 | 507614.2132 | 7614.2132 | 65989.8477 | 573604.0609 | 2025-02-17 | NO |  | NO
42 | Sanjen(78MW) | Salasungi Power Pvt Ltd | Powerhouse | Er. Sumit Sah |  |  | 2025-01-07 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 3352000 | 3403045.6853 | 51045.6853 | 442395.9391 | 3845441.6244 | 2024-12-18 | YES | 2024-12-24 | NO
43 | New Marshyangdi |  | Substation | Er. Ram Sharan Timilsina |  |  |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6102000 | 6194923.8579 | 92923.8579 | 805340.1015 | 7000263.9594 | 2025-01-09 | NO |  | NO
44 | Khimti 2(48.8MW) | Peoples Energy Limited | Powerhouse | Er. Ram Sharan Timilsina |  |  | 2025-02-12 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-03 | NO |  | NO
45 | Bhimsensthan (Khimti Garjyang LILO) | Peoples Energy Limited | Substation | Er. Ram Sharan Timilsina |  |  | 2025-02-13 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2025-01-03 | NO |  | NO
46 | Upper Bhotekoshi (45MW) | Bhotekoshi Power Company Pvt.Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-01-28 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 |  | NO |  | NO
47 | Karuwa Seti(32MW) | Jhyamolongma Hydropower Development Company Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-02-16 |  | FALSE | FALSE | FALSE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2025-01-28 | NO |  | NO
48 | Lower Erkhuwa(14.1MW) | Lower Erkhuwa Hydropower Company Ltd | Powerhouse | Er. Sumit Sah |  |  | 2025-02-20 |  | FALSE | FALSE | FALSE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-02-10 | NO |  | NO
49 | Kabeli -3(21.93MW) | Kabeli Hydropower Company Ltd. | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned |  | 0 | 0 | 0 | 0 |  | NO |  | NO
50 | Kabeli Khola "A" (13.5MW) | Snow Rivers Limited | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned |  | 0 | 0 | 0 | 0 |  | NO |  | NO
51 | Kabeli Khola "A" (12 MW) | Hilton Hydro Energy Limited | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned |  | 0 | 0 | 0 | 0 |  | NO |  | NO
52 | Upper Chaku "A" (22.2MW) | Shiva Shree Hydropower (Pvt) Ltd | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned |  | 0 | 0 | 0 | 0 |  | NO |  | NO
53 | Burtibang Substation | Burtibang- Paudi Amarai- Tamghas- Sandhikharka- Gurusinghe 132kV TL Project | Substation | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 |  | NO |  | NO
54 | Paudi Amarai Substation | Burtibang- Paudi Amarai- Tamghas- Sandhikharka- Gurusinghe 132kV TL Project | Substation | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 |  | NO |  | NO
55 | Birauta | Urban Transmission and Distribution System Improvement Project | Substation | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned | 3352000 | 3403045.6853 | 51045.6853 | 442395.9391 | 3845441.6244 |  | NO |  | NO
56 | Lower Solu (82MW) | Solu Hydropower Limited | Powerhouse | [5 empty] | FALSE | FALSE | FALSE | FALSE | Not Assigned |  | 0 | 0 | 0 | 0 |  | NO |  | NO
57 | Amlekhgunj Substation | Amlekhgunj 132kV Substation Construction Project | Substation | [5 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 | 0 | 0 | 0 |  | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE | In Progress |  | 0 |  | 0 | 0 |  | NO |  | NO
[13 empty] | Total | 164544003 | 167049749.2386 | 2505746.2386 | 21716467.401 | 188766216.6396
[13 empty] | Deposited | 43632000 | 45819289.3401 | 687289.3401 | 5956507.6142 | 51775796.9543 |  | 16

## Sumit (hidden)
ID | Project Name | Company/Project | Type | Engineer1 | Engineer2 | TFC | StartDate | EndDate | IFS | Network | Graphics | P2P | Status | Service Charge Ex.TDS | Service Charge Inc.TDS | TDS @1.5% | VAT @13% | Service Charge Inc.VAT | Informed Date | Amount Deposited? | Deposited Date | Final Bill Issued?
1 | Middle Modi(18MW) | Middle Modi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-04-25 | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-02 | NO |  | NO
2 | Upper Chameliya (40MW) | Api Chameliya Power Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-24 | YES | 2025-02-03 | NO
3 | Upper Tamakoshi(456MW) | Upper Tamakoshi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 5352000 | 5433502.5381 | 81502.5381 | 706355.3299 | 6139857.868 | 2025-01-02 | NO |  | NO
4 | Lower Modi (20MW) | Modi Energy Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-05-09 | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-26 | NO |  | NO
5 | Upper Balefi(36MW) | Balefi Hydropower Limited | Powerhouse | Er. Sumit Sah |  | 0 |  | 2024-06-24 | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-02 | YES | 2025-01-25 | NO
6 | Upallo Khimti (12MW) | Himalay Urja Bikas Company Limited | Powerhouse | Er. Sumit Sah |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | YES | 2025-02-03 | NO
7 | New Khimti 220kV |  | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed |  | 0 | 0 | 0 | 0 |  | NO |  | NO
8 | New Hetauda 220kV | Nepal India Power Transmisson and Trade Project | Substation | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 4602000 | 4672081.2183 | 70081.2183 | 607370.5584 | 5279451.7766 | 2025-01-10 | NO |  | NO
9 | Loharpatti | Dhalkebar Loharpatti 132kV Transmission line Project | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  | 2025-01-27 | TRUE | TRUE | TRUE | TRUE | Completed | 3852000 | 3910659.8985 | 58659.8985 | 508385.7868 | 4419045.6853 | 2025-01-10 | NO |  | NO
10 | Inaruwa 220kV | Nepal India Power Transmisson and Trade Project | Substation | Er. Sumit Sah |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-10 | NO |  | NO
11 | New Bharatpur 220kV | Marshyangdi Corridor 220kV TL Project | Substation | Er. Sumit Sah |  | 0 | 2024-12-17 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-09 | NO |  | NO
12 | Rasugadhi(111MW) | Rasuwagadhi Hydropower Company Limited | Powerhouse | Er. Sumit Sah |  | 0 | 2024-12-31 | 2025-01-07 | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2024-12-26 | YES | 2024-12-31 | NO
13 | DownPiluwa (10.3MW) | River Falls Power Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-01-07 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-10 | YES |  | NO
14 | Langtang(20MW) | Multi Energy Development P. Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-02-11 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602002 | 2641626.3959 | 39624.3959 | 343411.4315 | 2985037.8274 | 2024-12-10 | NO |  | NO
15 | Sanjen(78MW) | Salasungi Power Pvt Ltd | Powerhouse | Er. Sumit Sah |  |  | 2025-01-07 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 3352000 | 3403045.6853 | 51045.6853 | 442395.9391 | 3845441.6244 | 2024-12-18 | YES | 2024-12-24 | NO
16 | Upper Bhotekoshi (45MW) | Bhotekoshi Power Company Pvt.Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-01-28 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 |  | NO |  | NO
17 | Karuwa Seti(32MW) | Jhyamolongma Hydropower Development Company Limited | Powerhouse | Er. Sumit Sah |  |  | 2025-02-16 |  | FALSE | FALSE | FALSE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2025-01-28 | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE

## Janardhan Rimal (hidden)
ID | Project Name | Company/Project | Type | Engineer1 | Engineer2 | TFC | StartDate | EndDate | IFS | Network | Graphics | P2P | Status | Service Charge Ex.TDS | Service Charge Inc.TDS | TDS @1.5% | VAT @13% | Service Charge Inc.VAT | Informed Date | Amount Deposited? | Deposited Date | Final Bill Issued?
1 | Nilgiri 2 (71MW) | Nilgiri Khola Hydropower Company Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  | 2024-04-03 | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-26 | YES | 2025-02-03 | NO
2 | Likhu 1 | Pan Himalaya Energy Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3602000 | 3656852.7919 | 54852.7919 | 475390.8629 | 4132243.6548 | 2024-12-31 | YES | 2025-02-11 | NO
3 | Upper Kalangagad (38MW) | Sanigad Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-31 | NO |  | NO
4 | Upper Sanigad(10.7MW) | Bungal Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-31 | NO |  | NO
5 | Kalanga(15MW) | Kalanga Hydro Pvt. Limited | Powerhouse | Er. Janardan Rimal |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
6 | Super Madi(44MW) | Super Madi Hydropower Limited | Powerhouse | Er. Janardan Rimal |  |  |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-03 | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE

## Neha (hidden)
ID | Project Name | Company/Project | Type | Engineer1 | Engineer2 | TFC | StartDate | EndDate | IFS | Network | Graphics | P2P | Status | Service Charge Ex.TDS | Service Charge Inc.TDS | TDS @1.5% | VAT @13% | Service Charge Inc.VAT | Informed Date | Amount Deposited? | Deposited Date | Final Bill Issued?
1 | Dudhkunda(12MW) | Mount Everest Power Development Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | NO |  | NO
2 | Dordi 1(12MW) | Dordi Khola Jalavidhyut Compani Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
3 | Upper Solu(19.8MW) | Beni Hydropower Project Limited | Powerhouse | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2024-12-26 | YES |  | NO
4 | Tamghas 132kV | Burtibang Paudi Amarai Tamghas 132kV TL Project | Substation | Er. Neha Karn | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-09 | NO |  | NO
5 | Trishuli 3B 220kV |  | Substation | Er. Neha Karn |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6352000 | 6448730.9645 | 96730.9645 | 838335.0254 | 7287065.9898 | 2025-01-09 | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE

## Ramsharan (hidden)
ID | Project Name | Company/Project | Type | Engineer1 | Engineer2 | TFC | StartDate | EndDate | IFS | Network | Graphics | P2P | Status | Service Charge Ex.TDS | Service Charge Inc.TDS | TDS @1.5% | VAT @13% | Service Charge Inc.VAT | Informed Date | Amount Deposited? | Deposited Date | Final Bill Issued?
1 | Middle Modi(18MW) | Middle Modi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-04-25 | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-02 | NO |  | NO
2 | Ghar Khola (14 MW) | Myagdi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-06-03 | TRUE | TRUE | TRUE | TRUE | Completed | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-26 | YES | 2025-02-07 | NO
3 | Upper Chameliya (40MW) | Api Chameliya Power Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-24 | YES | 2025-02-03 | NO
4 | Upper Tamakoshi(456MW) | Upper Tamakoshi Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 5352000 | 5433502.5381 | 81502.5381 | 706355.3299 | 6139857.868 | 2025-01-02 | NO |  | NO
5 | Lower Modi (20MW) | Modi Energy Limited | Powerhouse | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  | 2024-05-09 | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-26 | NO |  | NO
6 | Maya Khola (14MW) | Maya Khola Hydropower Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-07 | NO |  | NO
7 | Nilgiri 1 | Nilgiri Khola Hydropower Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-31 | YES | 2025-02-03 | NO
8 | Middle Tamor(73MW) | Sanima Middle Tamor Hydropower Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-08-29 | TRUE | TRUE | TRUE | TRUE | Completed | 3602000 | 3656852.7919 | 54852.7919 | 475390.8629 | 4132243.6548 | 2024-12-26 | NO |  | NO
9 | Matatirtha 220kV |  | Substation | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 7102000 | 7210152.2843 | 108152.2843 | 937319.797 | 8147472.0812 | 2025-01-09 | NO |  | NO
10 | New Khimti 220kV |  | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed |  | 0 | 0 | 0 | 0 |  | NO |  | NO
11 | New Hetauda 220kV | Nepal India Power Transmisson and Trade Project | Substation | Er. Ram Sharan Timilsina | Er. Sumit Sah | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 4602000 | 4672081.2183 | 70081.2183 | 607370.5584 | 5279451.7766 | 2025-01-10 | NO |  | NO
12 | Tallo Khare(11MW) | Universal Power Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | NO |  | NO
13 | Arun 3 ,Dhalke 400kV Extension | SJVN Arun-3 Power Development Company Pvt Ltd | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-09-25 | TRUE | TRUE | TRUE | TRUE | Completed | 3250000 | 3299492.3858 | 49492.3858 | 428934.0102 | 3728426.3959 | 2025-01-11 | NO |  | NO
14 | Mathillo Mailung(14.3MW) | Mathillo Mailun Khola Jalvidhyut Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-31 | NO |  | NO
15 | Seti Nadi (25MW) | Vision Lumbini Urja Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 |  | 2024-11-24 | TRUE | TRUE | TRUE | TRUE | Completed | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2024-12-26 | NO |  | NO
16 | Loharpatti | Dhalkebar Loharpatti 132kV Transmission line Project | Substation | Er. Sumit Sah | Er. Ram Sharan Timilsina | 0 |  | 2025-01-27 | TRUE | TRUE | TRUE | TRUE | Completed | 3852000 | 3910659.8985 | 58659.8985 | 508385.7868 | 4419045.6853 | 2025-01-10 | NO |  | NO
17 | Udipur | Marshyangdi Corridor 220kV TL Project | Substation | Er. Ram Sharan Timilsina |  | 0 | 2024-11-24 |  | TRUE | TRUE | TRUE | TRUE | Completed | 5602000 | 5687309.6447 | 85309.6447 | 739350.2538 | 6426659.8985 | 2025-01-09 | NO |  | NO
18 | Tamghas 132kV | Burtibang Paudi Amarai Tamghas 132kV TL Project | Substation | Er. Neha Karn | Er. Ram Sharan Timilsina | 0 |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 3102000 | 3149238.5787 | 47238.5787 | 409401.0152 | 3558639.5939 | 2025-01-09 | NO |  | NO
19 | Chilime Hub 220kV |  | Substation | Er. Ram Sharan Timilsina |  | 0 | 2024-11-28 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 5102000 | 5179695.4315 | 77695.4315 | 673360.4061 | 5853055.8376 | 2025-01-09 | NO |  | NO
20 | Sanjen (42.5MW) | Sanjen Jalvidyut Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 | 2024-12-08 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2024-12-13 | YES | 2024-12-17 | NO
21 | Sanjen Upper (14.8MW) | Sanjen Jalvidyut Company Limited | Powerhouse | Er. Ram Sharan Timilsina |  | 0 | 2024-12-08 | 2024-12-23 | TRUE | TRUE | TRUE | TRUE | Completed | 2352000 | 2387817.2589 | 35817.2589 | 310416.2437 | 2698233.5025 | 2024-12-13 | YES | 2024-12-17 | NO
22 | Mathillo Mardi(7)+ Mardi(4.8MW) | United IDI Mardi and RB Hydropower Ltd | Powerhouse | Er. Ram Sharan Timilsina |  |  |  |  | TRUE | TRUE | TRUE | TRUE | Completed | 250000 | 253807.1066 | 3807.1066 | 32994.9239 | 286802.0305 |  | NO |  | NO
23 | New Marshyangdi |  | Substation | Er. Ram Sharan Timilsina |  |  |  |  | TRUE | TRUE | TRUE | FALSE | In Progress | 6102000 | 6194923.8579 | 92923.8579 | 805340.1015 | 7000263.9594 | 2025-01-09 | NO |  | NO
24 | Khimti 2(48.8MW) | Peoples Energy Limited | Powerhouse | Er. Ram Sharan Timilsina |  |  | 2025-02-12 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2602000 | 2641624.3655 | 39624.3655 | 343411.1675 | 2985035.533 | 2025-01-03 | NO |  | NO
25 | Bhimsensthan (Khimti Garjyang LILO) | Peoples Energy Limited | Substation | Er. Ram Sharan Timilsina |  |  | 2025-02-13 |  | TRUE | TRUE | TRUE | FALSE | In Progress | 2852000 | 2895431.4721 | 43431.4721 | 376406.0914 | 3271837.5635 | 2025-01-03 | NO |  | NO
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE | [5 empty] | 93777380.7107
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE
[9 empty] | FALSE | FALSE | FALSE | FALSE